## QA Build1
S. No. | Modules | Issue Description | Priority | Defect Status
1 | Web Login functionality | Forgot Password is not working, Email is not getting sent to the registered user email address. | High | Open
2 |  | When logged in user copy URL and paste in new browser window, it is not redirecting to Login page | Low | Fixed
3 |  | After logout if user clicks on back button of the browser, user is still logged in within same session. Instead, it should redirect to login page. | Medium | Fixed
4 |  | User should not be allowed to log in with different credentials from the same browser at the same time. | Low | Open
5 |  | Cancel button on New user registration is not working as expected rather it is working as a reset button on the page | Medium | Fixed
6 | User Management | Getting below error upon new user creation with admin user- "Contact to administrator or please check email settings." | Medium | Open
|  | Cancel button on Add New user pop up is not working as expected rather it is working as a reset button on the page | Medium | Fixed
7 |  | New User is getting created in the application but present in 'Inactive' status instead of 'Pending' | Medium | Fixed
8 |  | Edit button on Edit User details pop up is not working when the Email value is more than 25 characters | Medium | Fixed
9 |  | Email address field is accepting wrong value like "testuser@in" | Low | Open
10 |  | Throwing error on Email 'Email address can not exceed 80 letters.' though the characters are less than 80 | Medium | Fixed
11 |  | Application is getting hanged upon clicking on Cancel button on Unlock user pop up. | Medium | Fixed
12 | Item Category, Item SubCategory, Item Type, Manage Item, Manage Supplier, Manage Warehouse, Manage Location, Manage Role | Cancel button on Add New Item Category pop up is not working as expected rather it is working as a reset button on the page. (Same for other modules mentioned) | Medium | Fixed
13 | Item Type, Manage Item | On Add new Item Type pop up, Sub-Category dropdown is not working. | High | Fixed
14 | Manage Supplier Item | Last Ordered Date is accepting future date | Medium | Open
15 | Manage Supplier Item | Note Content value is not displayed in the Manage Supplier Item grid | Low | Open
16 | Manage Supplier Item | On Edit Supplier Item pop up, the value of 'Last Ordered' field is not displayed | Medium | Open
17 | Manage Supplier Item, Manage Location Item | Back button on Manage Supplier Item is navigating to Manage Item page instead of Manage Presentation Item page | Low | Open
18 | Manage Location Item | On Edit Location Item details pop up, System is getting hanged upon clicking on Edit button | High | Open