## Defect Log
Bug # | Test Case ID | Module Name | Defect Description | Priority | Date Opened | Defect Status
1 | TC_06 | Web Login | Forgot Password is not working, Email is not getting sent to the registered user email address. | High | 2021-11-08 | Closed
2 | TC_08 | Web Login | When logged in user copy URL and paste in new browser window, it is not redirecting to Login page | Low | 2021-11-08 | Closed
3 | TC_09 | Web Login | After logout if user clicks on back button of the browser, user is still logged in within same session. Instead, it should redirect to login page. | Medium | 2021-11-08 | Closed
4 | TC_14 | Web Login | User should not be allowed to log in with different credentials from the same browser at the same time. | Low | 2021-11-08 | Open
5 | TC_16 | Web Login | Cancel button on New user registration is not working as expected rather it is working as a reset button on the page | Medium | 2021-11-08 | Closed
6 | TC_05 | User Management | Getting below error upon new user creation with admin user- "Contact to administrator or please check email settings." | Medium | 2021-11-08 | Closed
7 | TC_04 | User Management | Cancel button on Add New user pop up is not working as expected rather it is working as a reset button on the page | Medium | 2021-11-08 | Closed
8 | TC_06 | User Management | New User is getting created in the application but present in 'Inactive' status instead of 'Pending' | Medium | 2021-11-09 | Closed
9 | TC_07 | User Management | Edit button on Edit User details pop up is not working when the Email value is more than 25 characters | Medium | 2021-11-09 | Closed
10 | TC_07 | User Management | Email address field is accepting wrong value like "testuser@in" | Low | 2021-11-09 | Closed
11 | TC_07 | User Management | Throwing error on Email 'Email address can not exceed 80 letters.' though the characters are less than 80 | Medium | 2021-11-10 | Closed
12 | TC_11 | User Management | Application is getting hanged upon clicking on Cancel button on Unlock user pop up. | Medium | 2021-11-10 | Closed
13 | TC_04 | Item Category, Item SubCategory, Item Type, Manage Item, Manage Supplier, Manage Warehouse, Manage Location, Manage Role | Cancel button on Add New Item Category pop up is not working as expected rather it is working as a reset button on the page. (Same for other modules mentioned) | Medium | 2021-11-11 | Closed
14 | TC_05 | Item Type, Manage Item | On Add new Item Type pop up, Sub-Category dropdown is not working. | High | 2021-11-11 | Closed
15 | TC_26 | Manage Supplier Item | Last Ordered Date is accepting future date | Medium | 2021-11-12 | Closed
16 | TC_26 | Manage Supplier Item | Note Content value is not displayed in the Manage Supplier Item grid | Low | 2021-11-12 | Closed
17 | TC_26 | Manage Supplier Item | On Edit Supplier Item pop up, the value of 'Last Ordered' field is not displayed | Medium | 2021-11-12 | Closed
18 |  | Manage Supplier Item, Manage Location Item | Back button on Manage Supplier Item is navigating to Manage Item page instead of Manage Presentation Item page | Low | 2021-11-12 | Closed
19 | TC_37 | Manage Location Item | On Edit Location Item details pop up, System is getting hanged upon clicking on Edit button | High | 2021-11-12 | Closed
20 | TC_03 | Purchase Order | On create new order page, the Supplier name is appearing twice in the dropdown field | Low | 2021-11-15 | Closed
21 | TC_03 | Purchase Order | On create new order page, under action button -> in Item help pop up, the field values are showing twice | Low | 2021-11-15 | Closed
22 | TC_03 | Purchase Order | On Create new order page, the dropdown field 'Assigned To (Approval)' is showing Inactive users also | Medium | 2021-11-16 | Closed
23 |  | Purchase Order | Create new order page is not working when performing below steps: 1. Login with Purchase Team user 2. Navigate to PO list 3. Select 'Approved' in the filter dropdown 4. Click on Action button of the order displayed and select view 5. Click on Cancel 6. Now click on 'Create new order' button | High | 2021-11-16 | Closed
24 |  | Purchase Order | On Purchase Order page, the filter default value is set as 'Save as draft' | Low | 2021-11-16 | Closed
25 |  | Web Login | Timeout Case: After putting application idle for sometime and then try to create or update any entity, user get logged out of the application but the entity pop up/screen remains open and no other action gets performed | Medium | 2021-11-16 | Fixed
26 |  | Purchase Order | When warehouse is not selected and user clicks on PO list, warehouse pop up opens. After selecting a warehouse, user is not getting navigated to the PO page automatically instead user has to click again on PO list. | Medium | 2021-11-16 | Closed
27 |  | Purchase Order | In case of 'Change Request' operation, user does not have option to change the order and resubmit again for the approval | Medium | 2021-11-16 | Closed
28 |  | Web Login | User is unable to login after password reset | High | 2021-11-19 | Closed
29 | TC_12 | Item In/Out | Dropdown fields on Item In/Out page is not getting cleared upon changing the value of Category Steps to follow: 1. Login with Forklift driver 2. Go to Item In/Out -> Select from the list 3. Select Category, subcategory, type, Item, Presentation 4. Now, change the value of category dropdown It should reset the other dropdown fields values | Low | 2021-11-22 | Closed
30 | TC_10 | Item In/Out | User is able to withdraw '0' item from the inventory | Low | 2021-11-22 | Closed
31 | TC_11 | Item In/Out | User is able to return '0' item into the inventory | Low | 2021-11-22 | Closed
32 | TC_13 | Item In/Out | On Item In/Out page, upon changing location, the field values are not getting changed | Medium | 2021-11-22 | Closed
33 | TC_03 | Purchase Order | On Create New Order page, Shipping address field mandatory behavior is not working as expected Steps to reproduce: 1. Login with Purchase Team user 2. Go to PO page -> Create new order button 3. Keep Shipping address field blank 4. Select and enter value in all fields except Shipping address 5. Click on Send for approval 6. Click Yes on confirmatory pop up PO order gets created and send for approval. | Low | 2021-11-25 | Closed
34 | TC_04 | Purchase Order | Once the new order is created, user remains on the Create new order page. Also, the value of Total does not get reset after new order creation. Steps to reproduce: 1. Login with Purchase Team user 2. Go to PO page -> Create new order button 3. Create new order (either in Save as draft or Send for approval) 4. Check that user is still on the Create new order page and the value of total is from the last order creation. | Medium | 2021-11-25 | Closed
35 | TC_09 | Purchase Order | On View Purchase Order page, Created by field value is blank Steps to reproduce: 1. Login with Purchase Team user 2. Go to PO page 3. Select PO and click on View action button | Medium | 2021-11-25 | Closed
36 |  | Purchase Order | On create new Order page, after entering item quantity as '0' or blank, the total amount shows as '$NaN. Also, when user tries to create order with the same value, error 400 occurred. | Medium | 2021-11-26 | Closed
37 | TC_08 | Manage Item Type | After unlocking item type, the inactive filter page is not getting refreshed and updated Steps to reproduce: 1. Login with admin user 2. Go to Manage Item Type 3. Select any active Item type and lock it 4. Change the filter to 'Inactive' 5. Now, select that inactive item type and unlock it It should be gone to the Active list but it is still displayed under Inactive filter. | Medium | 2021-11-26 | Closed
38 | TC_10 | Manage Item Type | On Manage item type page, the Status filter is not working properly Steps to reproduce: 1. Login with admin user 2. Go to Manage Item Type 3. Change the filter from 'Active' to 'Inactive' It is not changing the grid and showing Active values only. | Medium | 2021-11-26 | Closed
39 | TC_05 | Manage Item | New Item is not getting created with blank description value. Throwing error as 'Item description: is already exist'. Steps to reproduce: 1. Login with admin user 2. Go to Manage Item 3. Click on Add new item button 4. Enter value in mandatory fields, keep Description as blank 5. Click on Save button 6. Click Save on confirmatory pop up Error displayed. | Medium | 2021-11-26 | Closed
40 | TC_08 | Manage Item | User is not able to unlock item. Throwing error as 'Enter valid item id.'. | High | 2021-11-26 | Closed
41 | TC_13 | Purchase Order | Billing address selected by user is not getting saved instead it is taking the default one while editing the same order. Steps to reproduce: 1. Login with Purchase Team user 2. Go to PO List 3. Click on Create Order button 4. Select billing address other than the default one 5. Save it 6. Now, edit the same order and verify that the billing address is the default address. Similarly, after adding/removing item details row and click on Save as draft button, it is not saving as expected. | Medium | 2021-11-29 | Closed
42 |  | Transfer Queue | Filter value is set as 'Pending' by default, it should be 'All'. | Low | 2021-11-29 | Closed
43 | TC_05 | Transfer Queue | on Transfer Item page, 'Assign To' field is appearing twice | Low | 2021-11-29 | Closed
44 |  | Transfer Queue | No action options are appearing for 'Pending' Transfer queue requests | High | 2021-11-29 | Closed
45 | TC_17 | Purchase Order | Canceled status PO should not have option to save as draft again | Medium | 2021-11-30 | Closed
46 |  | Inventory List/Transfer Queue | The column names like 'Qty.' should be displayed completely | Low | 2021-11-30 | Closed
47 |  | Purchase Order | Purchase Team user is able to create purchase order with inactive item (or item type, presentation) Steps to reproduce: 1. Login with Purchase Team user 2. Go to PO List 3. Click on Create Order 4. Select supplier and other details 5. Enter Item code of an inactive item or search item through search icon 6. Click on send for approval | High | 2021-11-30 | Closed
48 |  | Purchase Order | Filters should remain same until user changes it manually Steps to reproduce: 1. Login with admin 2. Go to PO List 3. Change the filter from 'My Orders' to 'Other Orders' 4. Now, perform any operation on a row 5. Check that the filter value gets reset to 'My Orders' | Low | 2021-11-30 | Closed
49 | TC_11 | Purchase Order | Error 400 found when user saves Purchase order without adding quantity in the Item Steps to reproduce: 1. Login with Purchase Team user 2. Go to PO List 3. Click on Create Order 4. Select supplier and other details 5. Enter item code and keep quantity as blank 6. Click on Save as draft button | High | 2021-11-30 | Closed
50 | TC_11 | Purchase Order | On Create Order page, 'Save as draft' button should be enabled as soon as any one field is populated | Medium | 2021-11-30 | Closed
51 |  | Purchase Order | A PO user should not perform any operation except View on the PO created by other user | Medium | 2021-12-01 | Closed
52 |  | Inventory List | Incorrect arrow signs are displayed on Inventory list | Medium | 2021-12-01 | Closed
53 |  | Transfer Queue | User is able to transfer an inactive Item | Medium | 2021-12-01 | Closed
54 |  | Manage Item | Validation message does not appear upon giving threshold value more than minimum quantity | Medium | 2021-12-01 | Closed
55 | TC_02 | Purchase Order | UI Discrepancies: 1. Assign for approval and assign to approval 2. View Purchase Order and Edit Order 3. Approval Pending and Pending Approval 4. Canceled and Cancelled | Low | 2021-12-01 | Closed
56 |  | Transfer Queue | The status of Transfer item request is not changing to 'Completed' in the first attempt due to which the item quantity is getting added twice at the receiver location. Steps to reproduce: 1. Login with Forklift driver 2. Go to Transfer Item 3. Create a new transfer item request 4. Go to Transfer Queue 5. Select the request created and change the status to moved 6. Refresh the page and go to Inventory list 7. Check that the inventory of sender side is updated and no update on receiver side 8. Again, go to Transfer Queue and change the request status from Moved to 'Completed' 9. Refresh the page and check the status is still 'Moved'. So try again to move the request to 'Completed'. 10. Go to Inventory and see that the receiver inventory is updated with value double than the requested. | High | 2021-12-02 | Closed
57 |  | Warehouse | Inactive Warehouse is also displayed in the Warehouse dropdown asked right after login into the application | Medium | 2021-12-02 | Closed
58 |  | Generic | Searched text is not getting cleared Steps to reproduce: 1. Login with admin 2. Go to Manage Warehouse 3. Enter text in the search box 4. Perform edit operation on the searched result 5. After saving the edited details, the grid shows all the rows and the searched text is still present in the box. | Medium | 2021-12-02 | Closed
59 |  | Item Type | The name of column 'Minimum Inv. quantity' on Add new Item type pop up should be displayed completely | Low | 2021-12-02 | Closed
60 |  | Inventory List | The column 'Supplier' on Inventory List Report is showing incorrect supplier value | Medium | 2021-12-02 | Rejected
61 |  | My Profile | With large Email address value of a user, the value of Email and Mobile on My Profile page is overlapping Refer user: qauser1/Driver@123 | Medium | 2021-12-02 | Closed
62 |  | Purchase Order | On create order page, item help pop up, validations are not working Steps to reproduce: 1. Login with Purchase Team user 2. Go to PO List 3. Click on Create Order button 4. Select supplier, click on item help action icon 5. Select Category and click on OK button Pop up gets closed. | Medium | 2021-12-03 | Closed
63 | TC_07 | Transfer Queue | On Transfer Item page, incorrect validation message 'From warehouse is required.' is displayed on field 'To Warehouse' | Low | 2021-12-03 | Closed
64 |  | Billing Address | Admin user is unable to create a new billing address - Error 404 occurred | High | 2021-12-06 | Closed
65 |  | Billing Address | Admin user is unable to update an existing billing address - getting below error: "Error occurred while updating billing address details." | High | 2021-12-06 | Closed
66 |  | Generic | Spelling of 'Activate' is incorrect in the Unlock warehouse, unlock location, unlock user pop ups. It is currently displayed as 'activete'. Also, the button name is 'Active warehouse' instead of 'Activate warehouse'. | Low | 2021-12-06 | Closed
67 |  | Generic | Validation message alignment is not proper. the words are overlapping with the textfield boundary. | Low | 2021-12-06 | Closed
68 | TC_19 (Manage User) | Generic | Sorting functionality is not working as expected. Like, it is not sorting the rows correctly if there are values in uppercase and lowercase | Medium | 2021-12-06 | Open
69 |  | Manage Supplier Item | For the newly created item presentation, found following issues: Item details are not loading. Field name is overlapping. Unable to create a new supplier item. | High | 2021-12-06 | Closed
70 |  | Manage Location Item | For the newly created item presentation, found following issues: Item details are not loading. Field name is overlapping. Unable to create a new location item. | High | 2021-12-06 | Closed
71 |  | Manage User | On Add new user pop up, the size of Status and Role dropdowns are smaller as compare to other fields | Low | 2021-12-06 | Closed
72 |  | Manage User | Message on Confirm Password field is not getting displayed when click on scroll bar | Low | 2021-12-06 | Closed
73 |  | Manage User | Approve User option is appearing for Active users. If click on it, it is navigating to the Edit User details page. | Medium | 2021-12-06 | Closed
74 |  | Transfer Item | On Transfer Item page, inactive warehouses are also appearing in the dropdown field. | Medium | 2021-12-06 | Closed
75 |  | Transfer Item | 1. Placement of field 'Location' is not appropriate. It should be aligned with other fields. 2. Placeholder text should be aligned properly 3. Message displayed on 'From location' field should have proper spacing. | Low | 2021-12-06 | Closed
76 |  | Item In/Out | Spacing between the fields should be consistent. | Low | 2021-12-06 | Closed
77 |  | Forgot Password | On Forgot Password page, the spacing between buttons and the alignment need to be corrected. | Medium | 2021-12-06 | Closed
78 |  | Transfer Queue | Spelling of assigned in the confirmatory pop up of change assign to should be displayed correctly. Currently, it is showing 'assgned'. Steps: 1. Login with Forklift driver 2. Go to Transfer Item -> create a new request 3. Go to Transfer Queue 4. Select the request and click on 'Change assign to' 5. Select user and click Submit | Low | 2021-12-06 | Closed
79 | TC_03 | Purchase Order | Fields alignment, text alignment on Create Purchase order page need to be done Shipping expected date field placement Item Code is overlapping with Item description | Low | 2021-12-06 | Closed
80 |  | Purchase Order | Purchase Order is getting send for approval without adding 'Shipping Expected Date' | Medium | 2021-12-06 | Closed
81 |  | New User Registration | If user is created through new user registration page and admin directly approves it without adding Role, then the user is not able to login after getting approved. | Medium | 2021-12-07 | Closed
82 |  | Purchase Order | Getting error on performing Change Request operation on Purchase Order | Medium | 2021-12-07 | Closed
83 |  | New User Registration | There should be spacing between Pomas icon and title 'New user registration' | Low | 2021-12-07 | Closed
84 |  | Generic | Screen resolution issues: Multiple scroll bars on login page Dashboard tab not seen clearly after login | Low | 2021-12-07 | Open
85 |  | Inventory List | Inventory Report page is not getting loaded | High | 2021-12-08 | Closed
86 |  | Purchase Order | Error400 occurred when trying to save invalid item details and quantity value on Create Purchase Order page Steps to reproduce: 1. Login with Purchase user 2. Go to Purchase Order 3. Click on Create Purchase Order button 4. Select Supplier and other details 5. Enter any random text in the Item code and give some quantity 6. Click on Save as draft button | Medium | 2021-12-08 | Closed
87 |  | Transfer Queue | User cannot see any action options for Pending requests until it is assigned to himself | Medium | 2021-12-09 | Closed
88 |  | Purchase Order | PO sent for approval without adding item details in it. Steps to reproduce: 1. Login with Purchase Team user 2. Go to Purchase Order 3. Click on Create Purchase Order button 4. Select Supplier, Assign to value 5. Click on Save as draft button 6. Select the same request and click action icon -> select 'Assign for approval' option 7. Select user and click Assign button | Medium | 2021-12-09 | Closed
89 |  | Item In/Out | Multiple rows are getting added for multiple transactions of same item in/out but there is no way to distinguish between them except the quantity. We can add transaction time along with date to resolve this. | Low | 2021-12-10 | Closed
90 |  | Generic | When we try to create a new entity and any error comes, it closes the pop up instead it should redirect to the pop up to change the required value. | Low | 2021-12-10 | Closed
91 |  | Generic | Lock/Unlock icon of all entities should be displayed correctly. | Low | 2021-12-10 | Closed
92 |  | Purchase Order | On Create Purchase Order -> item help pop up, Presentation value is not appearing in the dropdown | Medium | 2021-12-13 | Closed
93 |  | Purchase Order | On Create Purchase Order -> On removing item code, it does not reset other item details | Medium | 2021-12-13 | Closed
94 |  | Dashboard | Transfer Requests -> Moved Requests -> Action items (Change Assign To and Request Completed) are not working. Transfer Requests -> Pending Requests -> Action items (Change Assign To) is not working | Medium | 2021-12-13 | Closed
95 |  | Dashboard | With driver user, on Dashboard -> Transfer Requests -> Pending -> no action options are appearing | Medium | 2021-12-14 | Closed
96 |  | Dashboard | Threshold Limit -> One row is appearing in both categories 'Critical' and 'Warning'. (Conditions should be rechecked and worked as expected.) | Medium | 2021-12-14 | Closed
97 |  | Deficit Inventory | After saving the changes in the inventory, it comes to the grid with all values but the filter values remain display as previous one. Steps: 1. Login with Admin 2. Go to Deficit Inventory 3. Select filter values 4. Edit any row based on the filter results 5. After saving, check that the grid is refreshed but the filter values remain the same | Medium | 2021-12-14 | Closed
98 |  | Deficit Inventory | Dropdown fields on the page is not getting cleared/reset upon changing the value of Category or any other dropdown | Medium | 2021-12-14 | Closed
99 |  | Dashboard | Purchase Order should be displayes to admin Transfer Requests should be removed from the PO users dashboard | Medium | 2021-12-14 | Closed
100 |  | Purchase Order | User cannot add item on Purchase order which was saved initially without any item details Steps: 1. Login with Purchase user 2. Go to Purchase Order 3. Click on Create Purchase Order 4. Add all details except item 5. Click on Save as draft button 6. Edit this PO again and check that there is no option to add Item | Medium | 2021-12-15 | Closed
101 |  | Purchase Order | Error occurred while trying to save PO with item having 0 amount | Medium | 2021-12-16 | Closed
102 |  | Purchase Order | PO details are not getting downloaded on viewing Pending approval request with PO manager and change requested request with PO user | Medium | 2021-12-16 | Closed
103 |  | Purchase Order | Upon trying to edit Change requested PO with PO user, the details are not gettng downloaded | Medium | 2021-12-16 | Closed
104 |  | User Management | Multiple roles are displayed for a user Steps: 1. Login with admin 2. Go to User Manage User 3. Select user present in Pending status 4. Edit its role and save it 5. Now go to Dashboard, click on the users - new users grid will appear 6. Select the same user for which role was updated and lick on action button -> select Approve user 7. Select some other role and approve 8. Go to Manage User and check both roles are displayed for the new user | Medium | 2021-12-16 | Closed
105 | TC_17 | New User Registration | New user is getting created with different password and confirm password. Steps: 1. Launch url and click on 'create an account' link 2. Fill all the fields 3. Enter password (let say Admin@123) 4. Enter Confirm password different than password (let say Pomas@123) 5. Click on Create Account button 6. Check that new user account is created and is present in pending status | Medium | 2021-12-20 | Closed
106 |  | Barcode Generation | Barcode PDF is not getting generated for all items present in the application For example: Item '4688-MAS' | High | 2021-12-20 | Closed
107 |  | Barcode Generation | Generated barcodes are more than the number of copies asked by the user | Medium | 2021-12-20 | Closed
108 | TC_13 | Item In/Out | Driver user is not able to return or withdraw item from the location selected on the page Steps: 1. Login with Driver user 2. Go to Item In/Out 3. Select item from the list 4. Search through item code 5. Select other location from the dropdown and click on Return item button 6. Verify that the quantity and item location is the default one not the one selected by the user | Medium | 2021-12-21 | Closed
109 |  | Purchase Order | Tax applicable' checkbox is missing during Purchase order creation. It is appearing in edit mode. | Medium | 2022-01-03 | Closed
110 |  | Purchase Order | User is able to send PO for approval with inactive item | Medium | 2022-01-04 | Open
111 |  | Purchase Order | Approver user is unable to view 'Approve order' option for the Pending Approval PO with item quantity send as 0 | Medium | 2022-01-04 | Open
112 |  | Transfer Queue | On Request to attend tab, after we move the request to any status, 'logged by' column gets disappeared and it comes back after refreshing the page | Medium | 2022-01-06 | Open
113 |  | Purchase Order | Getting error on updating Expected delivery date of Purchase Order Steps: 1. Login with Purchase Team user 2. Create a new Purchase Order without adding expected delivery date and send for approval 3. Login with Manager user 4. Select the request in Pending approval and click on action icon 5. Select Change Expected Delivery Date option 6. Select the date and click on 'Change' button Result: No action performed | High | 2022-01-07 | Open
114 |  | Transfer Queue | Column 'To location' is not updating for some rows in the Completed requests grid | Medium | 2022-01-07 | Open
115 | TC_27 | Transfer Queue | Search is not working for Completed requests grid. It is only considering the first grid on My Requests tab | Medium | 2022-01-07 | Open
116 | TC_29 | Transfer Queue | Export List is not working for Completed requests grid. It is only considering the first grid on My Requests tab | Medium | 2022-01-07 | Open

## Analysis
Review Analysis
Cause Wise Defects Analysis |  | Severity Wise Defects Analysis |  | Defect Category Wise Analysis |  | Status Wise Defects Analysis
Defect Cause Category | No. of Defects | Defect Severity | No. of Defects | Defect Category | No. of Defects | Defect Status | No. of Defects
Environmental Issues | #REF! | Critical | #REF! | Functional | #REF! | Open | 1
Insufficient standards / processes / tools | #REF! | Major | #REF! | Requirement/Scope related | #REF! | Assigned | 0
Inadequate Inputs | #REF! | Minor | #REF! | Not Reproducible | #REF! | Fixed | 1
Inadequate Review of inputs | #REF! | Suggestion | #REF! | Suggestion | #REF! | Rejected | 0
Time constraint / Inflexible Schedules | #REF! | Query | #REF! | UI related (Look & Feel) | #REF! | Deferred | 0
Inadequate Skill levels/Improper Skill set | #REF! |  |  | Database related | #REF! | Closed | 43
Inadequate Training | #REF! |  |  | Environment Related | #REF!
Communication gap | #REF!
Unavailability of Resources | #REF!
Oversight | #REF!
Lack of Process Knowledge | #REF!
Improper Knowledge Transition | #REF!
Non standard templates | #REF!

## Guidelines
** Guidelines for filling key fields in the form along with description of different options provided within this. This will help defect reporter to fill form accurately and avoid any ambiguity
Field | Parameters | Description
Test Case ID |  | Mention the test case id for which this defect was identified
Module/Program Name |  | Name of the program/ Module in which this defect was discovered
Defect Description |  | Mention in brief what is the exact error that is coming
Defect Category | -
| Functional | Defect is related to functionality
| Requirement/Scope related | Defect is related to requirement or scope like missing requirement, misunderstood requirement etc.
| Not Reproducible | This defect cannot be reproduced.
| Suggestion | Just a suggestion.
| UI related (Look & Feel) | The finding is related to look & feel .
| Database related | Defect is related to database, wrong field mapping etc
| Environment Related | Defect is related to environment, like inappropriate environment configured/ mentioned .
Severity | - | This describes the impact of defect on the system/module
| Critical | Missing function / functionality. Defect has to be fixed before the work can proceed. Defect which acts as a Show Stopper
| Major | Defects that have to be corrected before product / project can function properly. However, the subsequent work can continue. Any defect that would result in a functionally incorrect behavior. Ex.: requirements not properly addressed, incorrect logic in low level design, omission of some key information in high level design, etc.
| Minor | Defects, which will not affect the functionality. A defect that is not severe enough to be classified as major, but which must be corrected anyway, is a minor defect. Readability problems, comment errors are some of the examples of minor defects.
| Suggestion | A suggestion is a recommendation to do something differently, that may or may not be implemented by the producer. Suggestions do not indicate a defect in the product.
| Query | Query is asking about some functionality that what is it intended to do in case a tester/ reviewer is not able to map it to appropriate requirement
Testing Type | - | Select Testing Type depending on stage where defect was detected
Date Opened | - | Date on which the defect was found
Priority | - | Select Priority for closing the defect mainly depending on the requirements of project
Assigned To |  | Name of the individual to whom the defect is assigned for resolution
Assigned Date |  | Date on which the defect is assigned for resolution
Expected resolution date |  | Date by which defect is expeceted to be resolved, this should be based on priority of defect.
Fixed on date |  | Date on which the defect was fixed
Defect Status | - | Status of defect will indicate current state of defect. Initially when it is logged all defects would have open status
| Open | When first time defect is logged by Tester
| Fixed | Change to this status when defect is reviewed by Author
| Assigned | Defect is assigned for fixing to developer
| Rejected | This will be status of defect when defect is discussed with tester and identified as not a defect
| Deferred | Change to this status when developer requires more clarification, awaiting response from stakeholder, fix is postponed to next cycle
| Closed | Defect is closed by the developer post correction
| In Progress | This will be the status of defect when it is being worked apon
| ReOpen | If defect has not been closed to satisfaction
Defect resolution action |  | Describe in brief the solution applied
Defect Cause | - | From drop down select the best cause which could have triggered to the defect
| Environmental Issues | Related to project environment settings, this covers problem related to domain knowledge, project team structure, management related issues etc.
| Insufficient standards / processes / tools | due to data, or due improper Hardware, Software compatibility
| Inadequate Inputs | Missing or wrong documents used for references or provided by client/external entity
| Inadequate Review of workproducts | Reviews of interim work products like design,test case review not performed or less time provided for conducting review
| Time constraint / Inflexible Schedules | Inadequate efforts provided for carrying out specific task from project schedule. This could lead to wron estimation of particular task
| Inadequate Skill levels/Improper Skill set | Skills required for executing tasks like design, coding not provided as planned/expected. For e.g. Java developer not having pre-requisite knowledge on struts
| Inadequate Training | Training not provided or provided but was not effective or not performed by appropriate person
| Communication gap | What was said got misinterpreted by team member. Lot of assumptions considered during communication due to unclear message from client, PM or other stakeholders. Some time this could be because communication not came at right time
| Unavailability of Resources | This is related to lack of tools or human resources for performing project tasks. E.g. nUnit not used on .Net project which led to lot of unit testing defects which could have been captured during coding phase only. Unavailability of human resources is different from lack of skills as here it talks about no. of resources provided for e.g. instead of 5 only 3 developer provided.
| Oversight/Negligence | Having knowledge how to perform particular task , but forgot to do it.
| Lack of Process Knowledge | Not aware about existence of certain process or steps for its execution
| Improper Knowledge Transition | Knowledge was not transferred to new resource or taking over resource because of which not got introduced to project environment
| Non standard templates | Standard used not proper or misguiding. Standards not in place
Phase Introduced In | - | Select appropriate phase of project where defect would have got introduced for the very first time. E.g. Field missing on form/screen could lead to design document which did not address particular field in Detailed Design/MD.070 document
Logged By | - | This should contain name of personwho identified the defect

## Version History
Version Control Sheet
Document Name |  | Defect Log
Document Number |  | FM-ENG-TST-02
Effective Date |  | 2017-09-15
Effective Version |  | 2.0
Author |  | Reviewer |  | Approver
Process Team |  | Process Champion |  | SEPG
Signature |  | Signature |  | Signature
Electronic copies valid without signature
<<This sheet is controlled by SEPG and shall not be violated by project in any case>>
Content Revision History
Version No. | Date Updated/ Released | Last Updated By | Nature of modification
0.1 | 2012-01-02 | SEPG | First draft
1 | 2012-01-17 | SEPG | Released to Organisation
1.1 | 2014-07-24 | SEPG | Modified as per review comments
1.2 | 2017-07-07 | Neha Chouhan | Created in Google doc, modified to mark mandatory fields, changes in severity, defect status, added guideline
1.3 | 2017-08-28 | Neha Chouhan | Modified as per review comments
2.0 | 2017-09-15 | SEPG | Released to Organisation
Master files are stored electronically and are available to all associates
Printed copies of the master files are for reference only.