## Defect Log
Bug # | Test Case ID | Module Name | Defect Description | Steps | Expected Result | Actual Result | Screencast | Priority | Date Opened | Defect Status
Bug_User01 | TC_UM01 | User Management | Field "User Role" gets blank when admin updates user data. | 1) Login into the system as an admin. 2) Navigate to the User Management section. 3) Select "All Warehouse" from the dropdown list of Warehouse. 4) Search "Issue" in the search bar. 5) Observe user "1vartmanissue". 6) Perform edit for the user. 7) Observe the Role of the user. | "Previously Saved" User role should not be removed, when admin performs edit/update for the user, also admin should be able to change the user role | Saved user role gets blank when admin performs edit for the user, and system asks user to select role. | https://www.screencast.com/t/5UozPNgRWk62 | Medium | 2022-01-07 | Closed
Bug_User02 | TC_UM02 | User Management | System accepts duplicate email address while updating the user data | 1) Login into the system as an admin. 2) Navigate to the User Management section. 3) Select "All Warehouse" from the dropdown list of Warehouse. 4) Search "Issue" in the search bar. 5) Observe user "1vartmanissue". 6) Perform edit/update for the user. 7) Update email address of the user with the one which already exists in our system. | System should not accept the email address which already exists in the system, system should not allow user to create/update 2 users with the same email address, email address should be unique same as the User name. | Unique email address check not working during the user profile update, system accepts duplicate email id while updating user profile. | https://www.screencast.com/t/5UozPNgRWk62 | High | 2022-01-15 | Closed
Bug_User03 | TC_UM03 | User Management | New user(Created by admin from the admin section) unable to login into the system with their credential. | 1) Login into the system as an admin. 2) Navigate to the User Management section. 3) Click on the Add user button. 4) Add new user into the system by providing all the mandatory information. 5) Click on Save button. 6) Once the user is created, try to login into the system with the same user id and credential that you have provided during the registration. 7) Observe the system behaviour. | User should be able to login into the system | User is unable to login into the system, system shows validation message Invalid credential. | https://www.screencast.com/t/YhGM5BSp3 | High | 2022-01-15 | Closed
[8 empty] | High | 2022-01-15 | Closed

## Analysis
Review Analysis
Cause Wise Defects Analysis |  | Severity Wise Defects Analysis |  | Defect Category Wise Analysis |  | Status Wise Defects Analysis
Defect Cause Category | No. of Defects | Defect Severity | No. of Defects | Defect Category | No. of Defects | Defect Status | No. of Defects
Environmental Issues | #REF! | Critical | #REF! | Functional | #REF! | Open | #REF!
Insufficient standards / processes / tools | #REF! | Major | #REF! | Requirement/Scope related | #REF! | Assigned | #REF!
Inadequate Inputs | #REF! | Minor | #REF! | Not Reproducible | #REF! | Fixed | #REF!
Inadequate Review of inputs | #REF! | Suggestion | #REF! | Suggestion | #REF! | Rejected | #REF!
Time constraint / Inflexible Schedules | #REF! | Query | #REF! | UI related (Look & Feel) | #REF! | Deferred | #REF!
Inadequate Skill levels/Improper Skill set | #REF! |  |  | Database related | #REF! | Closed | #REF!
Inadequate Training | #REF! |  |  | Environment Related | #REF!
Communication gap | #REF!
Unavailability of Resources | #REF!
Oversight | #REF!
Lack of Process Knowledge | #REF!
Improper Knowledge Transition | #REF!
Non standard templates | #REF!

## Guidelines
** Guidelines for filling key fields in the form along with description of different options provided within this. This will help defect reporter to fill form accurately and avoid any ambiguity
Field | Parameters | Description
Test Case ID |  | Mention the test case id for which this defect was identified
Module/Program Name |  | Name of the program/ Module in which this defect was discovered
Defect Description |  | Mention in brief what is the exact error that is coming
Defect Category | -
| Functional | Defect is related to functionality
| Requirement/Scope related | Defect is related to requirement or scope like missing requirement, misunderstood requirement etc.
| Not Reproducible | This defect cannot be reproduced.
| Suggestion | Just a suggestion.
| UI related (Look & Feel) | The finding is related to look & feel .
| Database related | Defect is related to database, wrong field mapping etc
| Environment Related | Defect is related to environment, like inappropriate environment configured/ mentioned .
Severity | - | This describes the impact of defect on the system/module
| Critical | Missing function / functionality. Defect has to be fixed before the work can proceed. Defect which acts as a Show Stopper
| Major | Defects that have to be corrected before product / project can function properly. However, the subsequent work can continue. Any defect that would result in a functionally incorrect behavior. Ex.: requirements not properly addressed, incorrect logic in low level design, omission of some key information in high level design, etc.
| Minor | Defects, which will not affect the functionality. A defect that is not severe enough to be classified as major, but which must be corrected anyway, is a minor defect. Readability problems, comment errors are some of the examples of minor defects.
| Suggestion | A suggestion is a recommendation to do something differently, that may or may not be implemented by the producer. Suggestions do not indicate a defect in the product.
| Query | Query is asking about some functionality that what is it intended to do in case a tester/ reviewer is not able to map it to appropriate requirement
Testing Type | - | Select Testing Type depending on stage where defect was detected
Date Opened | - | Date on which the defect was found
Priority | - | Select Priority for closing the defect mainly depending on the requirements of project
Assigned To |  | Name of the individual to whom the defect is assigned for resolution
Assigned Date |  | Date on which the defect is assigned for resolution
Expected resolution date |  | Date by which defect is expeceted to be resolved, this should be based on priority of defect.
Fixed on date |  | Date on which the defect was fixed
Defect Status | - | Status of defect will indicate current state of defect. Initially when it is logged all defects would have open status
| Open | When first time defect is logged by Tester
| Fixed | Change to this status when defect is reviewed by Author
| Assigned | Defect is assigned for fixing to developer
| Rejected | This will be status of defect when defect is discussed with tester and identified as not a defect
| Deferred | Change to this status when developer requires more clarification, awaiting response from stakeholder, fix is postponed to next cycle
| Closed | Defect is closed by the developer post correction
| In Progress | This will be the status of defect when it is being worked apon
| ReOpen | If defect has not been closed to satisfaction
Defect resolution action |  | Describe in brief the solution applied
Defect Cause | - | From drop down select the best cause which could have triggered to the defect
| Environmental Issues | Related to project environment settings, this covers problem related to domain knowledge, project team structure, management related issues etc.
| Insufficient standards / processes / tools | due to data, or due improper Hardware, Software compatibility
| Inadequate Inputs | Missing or wrong documents used for references or provided by client/external entity
| Inadequate Review of workproducts | Reviews of interim work products like design,test case review not performed or less time provided for conducting review
| Time constraint / Inflexible Schedules | Inadequate efforts provided for carrying out specific task from project schedule. This could lead to wron estimation of particular task
| Inadequate Skill levels/Improper Skill set | Skills required for executing tasks like design, coding not provided as planned/expected. For e.g. Java developer not having pre-requisite knowledge on struts
| Inadequate Training | Training not provided or provided but was not effective or not performed by appropriate person
| Communication gap | What was said got misinterpreted by team member. Lot of assumptions considered during communication due to unclear message from client, PM or other stakeholders. Some time this could be because communication not came at right time
| Unavailability of Resources | This is related to lack of tools or human resources for performing project tasks. E.g. nUnit not used on .Net project which led to lot of unit testing defects which could have been captured during coding phase only. Unavailability of human resources is different from lack of skills as here it talks about no. of resources provided for e.g. instead of 5 only 3 developer provided.
| Oversight/Negligence | Having knowledge how to perform particular task , but forgot to do it.
| Lack of Process Knowledge | Not aware about existence of certain process or steps for its execution
| Improper Knowledge Transition | Knowledge was not transferred to new resource or taking over resource because of which not got introduced to project environment
| Non standard templates | Standard used not proper or misguiding. Standards not in place
Phase Introduced In | - | Select appropriate phase of project where defect would have got introduced for the very first time. E.g. Field missing on form/screen could lead to design document which did not address particular field in Detailed Design/MD.070 document
Logged By | - | This should contain name of personwho identified the defect

## Version History
Version Control Sheet
Document Name |  | Defect Log
Document Number |  | FM-ENG-TST-02
Effective Date |  | 2017-09-15
Effective Version |  | 2.0
Author |  | Reviewer |  | Approver
Process Team |  | Process Champion |  | SEPG
Signature |  | Signature |  | Signature
Electronic copies valid without signature
<<This sheet is controlled by SEPG and shall not be violated by project in any case>>
Content Revision History
Version No. | Date Updated/ Released | Last Updated By | Nature of modification
0.1 | 2012-01-02 | SEPG | First draft
1 | 2012-01-17 | SEPG | Released to Organisation
1.1 | 2014-07-24 | SEPG | Modified as per review comments
1.2 | 2017-07-07 | Neha Chouhan | Created in Google doc, modified to mark mandatory fields, changes in severity, defect status, added guideline
1.3 | 2017-08-28 | Neha Chouhan | Modified as per review comments
2.0 | 2017-09-15 | SEPG | Released to Organisation
Master files are stored electronically and are available to all associates
Printed copies of the master files are for reference only.